## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Rishiraj Yadav | 2024-11-28 | Error in model accuracy using Whisper; replaced with Web Speech API. | Sprint 1 | Rishiraj Yadav | Functionality | Integrated Web Speech API to improve accuracy and resolved errors. | 2024-11-25 | Closed | API performs accurately without errors.
2 | Rishiraj Yadav | 2024-12-10 | Integrity issue: Data not being added to the cloud database using MySQL. | Sprint 2 | Rishiraj Yadav | Database | Switched to PostgreSQL for seamless cloud integration. | 2024-12-07 | Closed | Resolved with PostgreSQL integration.
3 | Rishiraj Yadav | 2024-12-15 | Delay in real-time processing for multilingual input. | Sprint 3 | Rishiraj Yadav | Performance | Optimized backend logic to reduce processing time. | 2024-12-12 | Closed | Improved response time significantly.
4 | Rishiraj Yadav | 2024-12-20 | Speech recognition fails intermittently in noisy environments. | Sprint 4 | Rishiraj Yadav | Functionality | Added noise cancellation preprocessing to improve input clarity. | 2024-12-18 | Closed | Noise handling is effective; performance improved.
5 | Rishiraj Yadav | 2024-12-22 | Frontend mic icon does not respond on some mobile browsers. | Sprint 5 | Rishiraj Yadav | UI/UX | Tested and fixed compatibility issues for different mobile browsers. | 2024-12-21 | Closed | Tested on all major mobile browsers; issue resolved.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others